## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | CampusPal: Generative AI-Driven Institutional Information Assistant |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P SHAH INSTITUTE OF TECHNOLOGY -CSE(AI&ML)
PROJECT GUIDE |  | Dr. Bharti Khemani |  |  |  |  | DATE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Days) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Identify project problem and objectives | All Members | 2025-07-07 |  | 1 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 2 W to WEEK 2 F
1.2 | Study existing chatbot and RAG systems | All Members |  |  | 1 | 100% | bar: WEEK 1 R to WEEK 1 F; WEEK 2 T; WEEK 2 R to WEEK 2 F
1.3 | Conduct literature survey (LLM + RAG) | Yash Desai |  |  | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.4 | Collect institutional data (APSIT website & PDFs) | Yash Desai |  |  | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.5 | Define system requirements and scope | Yash Desai |  |  | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.6 | Finalize project architecture concept | Yash Desai |  |  | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
2 | Project Design
2.1 | Design system architecture (RAG pipeline) | All Members |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 3 T
2.2 | Design data preprocessing pipeline | Pratik Dhas |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 3 W
2.3 | Design vector database structure (FAISS) | Vaibhav Bura |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 3 W to WEEK 3 F
2.4 | Design backend API workflow (FastAPI) | Pratik Dhas |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 3 W to WEEK 3 F
2.5 | Design frontend UI (React interface) | Vaibhav Bura |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 3 W to WEEK 3 F
2.6 | Define prompt engineering and agent workflow | Vivek Dalvi |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 3 W to WEEK 3 F
3 | Project Implementation
3.1 | Implement web scraping and data collection | Yash Desai |  |  | 4 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
3.2 | Implement data cleaning and text preprocessing | Pratik Dhas |  |  |  | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
3.3 | Implement embedding generation (MiniLM model) | Vaibhav Bura |  |  |  | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
3.4 | Setup FAISS vector database | Vaibhav Bura |  |  |  | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
3.5 | Develop backend APIs using FastAPI | Pratik Dhas |  |  |  | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
3.6 | Implement RAG pipeline with LangChain | Vivek Dalvi |  |  |  | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
3.7 | Integrate LLM (LLaMA via Groq API) | Vaibhav Bura |  |  |  | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
3.8 | Develop frontend UI using React | Vaibhav Bura & Yash Desai |  |  |  | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
3.9 | Integrate frontend with backend | Vivek Dalvi |  |  |  | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
3.1 | Perform system testing and debugging | Vivek Dalvi |  |  | 4 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 8 F
4 | Report and Research Paper Preparation
4.1 | Prepare research paper (all sections) | All Members |  |  | 1 | 100%
4.2 | Submit paper to conference | Vaibhav Bura |  |  |  | 100%
4.3 | Prepare blackbook (all chapters) | All Members |  |  |  | 100%
4.4 | Add diagrams, tables, and results | Yash Desai |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 2 F
4.5 | Incorporate guide feedback and corrections | All Members |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 2 F
4.6 | Final proofreading and formatting | Yash Desai |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 2 F
4.7 | Generate final report and submission | All Members |  |  | 1 | 100% | bar: WEEK 2 T to WEEK 2 F
100% | bar: WEEK 2 T to WEEK 2 F; WEEK 12 M to WEEK 12 F